## DBB Cost Estimate
Design-Bid-Build - Project Cost Estimate Summary
Project Name
Project Type | Conveyance Project |  | <---(pick from drop down list)
Estimator Name
Date of Estimate
Class of Estimate |  |  | <---(pick from drop down list)
Escalation Dates
| to Start Date of Const. | to Midpoint of Const.
Description |  |  | Conforms to PCM | Rate | Amount | Totals
Opinion of Probable Construction Cost (OPCC)
Cost of Work (COW):
Contractor COW (Labor, Materials, Equipment, Other Costs to Create Asset) |  |  |  |  | 1000000
General Conditions (% of COW per Table 2-2) |  |  |  | 0% | 0
Contractor's Overhead & Profit (% of COW per Table 2-2) |  |  |  | 0% | 0
Project Contingency (% of COW + markups by Estimate Class, per Table 2-3) |  |  |  | 0% | 0
|  | Construction Subtotal |  |  |  | 1000000
Insurance (1% of the Construction Subtotal) |  |  |  | 1% | 10000
Bonds (1% of the Construction Subtotal) |  |  |  | 1% | 10000
|  | Insurance & Bonds Subtotal |  |  |  | 20000
Escalation (To Midpoint of Construction - per MSD Escalation Table) |  |  |  |  | 0
|  | Esalation Subtotal |  |  |  | 0
Market Contingency (Consultant Evaluation) |  |  |  | 0% | 0
|  | Market Contingency Subtotal |  |  |  | 0
|  | OPCC Total |  |  |  | 1020000
Planning
Planning Services (Class 5: per formula included in Section 2.7.3; Class 1-4: Established/Actual) |  |  |  |  | 102392.2261
|  | Planning Subtotal |  |  |  | 102392.2261
Design
Design Services (Class 4-5: per formula included in Section 2.7.3; Class 1-3: Established/Actual) |  |  |  |  | 137449.4248
|  | Design Subtotal |  |  |  | 137449.4248
Pre-Construction Services
Pre-Construction Services (N/A for Design-Bid-Build) |  |  |  |  | 0
|  | Pre-Con Services Subtotal |  |  |  | 0 |  | calculated formula
Construction Services | [6 empty] | Conveyance Project | 104058.1176
Construction Services (Class 2-5: per formulas included in Section 2.7.3; Class 1: Established/Actual) |  |  |  |  | 104058.1176 |  | Facility Project without SCADA | 111897.8079
|  | Construction Services Subtotal |  |  |  | 104058.1176 | Facility Project with SCADA | 222407.9925
Right-of-Way
Right-of Way Costs (Class 3-5: per MSD ROW Manager; Class 1-2: Established/Actual)
Right-of-Way Costs Escalation (To Start Date of Construction - per MSD Escalation Table) |  |  |  |  | 0
|  | Right-of-Way Subtotal |  |  |  | 0
Miscellaneous Expense
Miscellaneous Expense (Class 4-5: per formulas included in Section 2.7.3; Class 1-3: Established/Actual) |  |  |  |  | 96711.0679
|  | Miscellaneous Expense Subtotal |  |  |  | 96711.0679
[5 empty] | Total Project Cost | 1460610.8364
* If any items are not selected, estimator to provide detailed explanation within the estimate submittal
Cost Summary (LAR Format)
| Planning | 102000
| Design | 137000
| Pre-Construction Services | 0
| Miscellaneous Expense | 96700
| Right-of-Way | 0
| Construction | 1020000
| Program Management | 0
| Construction Services | 104000
| Total Estimate | 1460000
Scope of Work Summary (Optional)
[insert scope of work summary]
*

## PDB Cost Estimate
Progressive Design-Build - Project Cost Estimate Summary
Project Name
Estimator Name
Date of Estimate
Class of Estimate |  |  | <---(pick from drop down list)
Escalation Dates
| to Start Date of Const. | to Midpoint of Const.
Description |  |  | Conforms to PCM | Rate | Amount | Totals
Opinion of Probable Construction Cost (OPCC)
Cost of Work (COW):
Design-Builder COW (Labor, Materials, Equipment, Other Costs to Create Asset) |  |  |  |  | 1000000
General Conditions (% of COW, per Table 2-2) |  |  |  | 0% | 0
Design-Build Services Fee (% of COW, per Table 2-2) |  |  |  | 0% | 0
Project Contingency (% of COW + markups by Estimate Class, per Table 2-3) |  |  |  | 0% | 0
Construction Subtotal | [5 empty] | 1000000
Insurance (1% of the Construction Subtotal) |  |  |  | 1% | 10000
Bonds (1% of the Construction Subtotal) |  |  |  | 1% | 10000
Insurance & Bonds Subtotal | [5 empty] | 20000
Escalation (To Midpoint of Construction - per MSD Escalation Table) |  |  |  |  | 0
Escalation Subtotal | [5 empty] | 0
MSD PDB Contingency (10% of Construction Subtotal, Bonds & Insurance, and Escalation) |  |  |  | 10% | 102000
Market Contingency (Consultant Evaluation) |  |  |  | 0% | 0
MSD PDB and Market Contingencies Subtotal | [5 empty] | 102000
OPCC Total | [5 empty] | 1122000
Planning
Planning Services (Class 5: per formula invluded in Section 2.7.3); Class 3-4: Established/Actual) |  |  |  |  | 108718.3829
|  | Planning Subtotal |  |  |  | 108718.3829
Design
Owner's Adviser Phase 1 Services (Class 4-5: See Table 2-3; Class 3: Established/Actual) |  |  |  | 1.5% | 16830
Design Services Fee (Class 4-5: per formula included in Section 2.7.3; Class 3: Established/Actual) |  |  |  |  | 147395.3439
|  | Design Subtotal |  |  |  | 164225.3439
Pre-Construction Services
Pre-Construction Fee (Class 4-5: See Table 2-3; Class 3: Established/Actual) |  |  |  | 3% | 33660
|  | Pre-Con Services Subtotal |  |  |  | 33660
Construction Services
Owner's Adviser Phase 2 Services (Class 3-5: See Table 2-3) |  |  |  | 0.5% | 5610
|  | Construction Services Subtotal |  |  |  | 5610
Right-of-Way
Right-of Way Costs (Class 3-5: per MSD ROW Manager) |  |  |  |  | 0
Right-of-Way Costs Escalation (To Start Date of Construction - per MSD Escalation Table) |  |  |  |  | 0
|  | Right-of-Way Services Subtotal |  |  |  | 0
Miscellaneous Expense
Miscellaneous Expense (Class 4-5: per formula included in Section 2.7.3; Class 3: Established/Actual) |  |  |  |  | 100201.5081
|  | Miscellaneous Expense Subtotal |  |  |  | 100201.5081
[5 empty] | Total Project Cost | 1534415.2349
* If any items are not selected, estimator to provide detailed explanation within the estimate submittal
Cost Summary (LAR Format)
| Planning | 108718.3829
| Design | 164225.3439
| Pre-Construction Services | 33660
| Miscellaneous Expense | 100201.5081
| Right-of-Way | 0
| Construction | 1122000
| Program Management | 0
| Construction Services | 5610
| Total Estimate | 1534415.2349
Scope of Work Summary (Optional)
*
[insert scope of work summary]

## Sheet1
Class 1 | Conveyance Project
Class 2 | Facility Project without SCADA
Class 3 | Facility Project with SCADA
Class 4
Class 5